## Slide 1: CMAM CONTINUUM OF CARE
COX’S BAZAR ROHINGYA RESPONSE,
BANGLADESH

## Slide 2: CMAM Continuum of Care
It is the linkage and integration among the 4 CMAM programme Components.
Community out-reach
In-patient Management of Severe Acute Malnutrition
Out-patient Management of Severe Acute Malnutrition
Management of Moderate Acute Malnutrition
It also entails the linkages of the CMAM programme to other complimentary and Preventive Services e.g
Linkage with health facilities for referring identified sick children
Linkages with IYCF and Blanket Supplementary Feeding Programmes

## Slide 3: Cox Bazar Context
According to Bangladesh’s Department of Immigration and Passports (DIP) there are 1,118,578 Rohingya in CXB.
Around 800,000 Rohingya Refugees arrived since 08/2017 Influx and reside in Makeshift/Spontaneous camps. This is in addition to the 300,000 Rohingyas that had arrived before with 33,956 Refugees already residing in Official camps.
The Rohingya’s who arrived in Oct – Dec 2016 and after August 2017 have no official refugee status in Bangladesh.
A National Guideline for CMAM exists but is hardly used in the rest of the Country. Bangladesh has no IYCF-E Operational Guideline
Notes: According to UNHCR population Figures 895,631 Rohingya Live in CXB, out of this 34,172 live in the Registered Camps. An average of 1,500 Rohingya arrive each month. Difference in data is because of merging individual data to constitute family units.
The CMAM guideline in Bangladesh places emphasis on home based treatment of acute malnutrition by use of local ‘food based recipes’ Halwa’ and ‘Kichuri”. A separate Guideline for Facility based treatment of complicated SAM exists and use of therapeutic Milks are allowed. Use of Kichuri and Halwa is only possible in regions where there is access to land and agricultural input ,in emergency situations this is not always possible and even worse in refugee context.
Community out-reach ,particularly active case, finding, referrals and defaulter tracing is not practiced in Bangladesh because of a number of limitations e.g No volunteer/community Network, limited bed capacity in hospital to treat all SAM cases out-patiently etc. SAM case identification is done through Facility based/ passive case finding
A draft IYCF-E Operational Guideline has been developed with the leadership of Nutrition Cluster
A SMART Survey and Rapid Nutrition Guideline exist, but needs to be updated. The quality assurance and validation protocol for assessments are not clearly outlined in the documents. No formal body for validation of Survey results.
.

## Slide 4: Nutrition Situation in Cox Bazar Rohingya Camps
Round one SMART Survey conducted in Oct-December 2017 depicted malnutrition levels of serious Public Health Significance.
Round 2 Survey conducted between May-July 2018 showed a slight reduction in acute malnutrition.
While modest gains in overall acute malnutrition prevalence were observed in Round 2, presence of malnutrition aggravating factors could worsen the situation if current efforts to treat and prevent under-nutrition are not intensified and sustained
Notes: In May 2017, prior to the recent influx of refugees, the GAM prevalence was 21.2% and the SAM prevalence was 3.6%.
Round 1 SMART Survey conducted between Oct-Dec 2017 indicated a Global Acute Malnutrition (GAM) rate of 24.3% and a Severe Acute Malnutrition (SAM) rate of 7.5% in Kutupalong refugee camp; a GAM rate of 19.3% and SAM rate of 3.0% in Makeshift Settlements and lastly a GAM rate of 14.3% and SAM rate of 1.3% in Nayapara refugee camp.
Round 2 SMART Survey indicate that the prevalence of global acute malnutrition among children aged 6-59 months using weight-for-height (WHZ) malnutrition indicator has decreased to below the WHO Emergency Threshold (15%) in the Makeshift settlements and Nayapara camps. A survey was not conducted in Kutupalong camp as Refugees refused to be measured or interviewed

## Slide 5: Coordination Structure in Cox Bazar
Notes: Include members of SEG
The SEG has the overall coordination mandate for Rohingya Refugee Response is the link to Ministry of Foreign Affairs
The Refugee Relief and Repatriation Commissioner (RRRC) leads the Government Coordination at CXB Level.
Senior Coordinator leads the ISCG Secretariat and ISCG Sector Coordination Group CXB.
ISCG is composed of 11 sector which are led by thematic Sector Coordinators.
Nutrition Sector is composed of 15 Members, 3 UN agencies, 8 INGOs and 4 NNGOs. DFID and ECHO are active donors and have representatives in the Nutrition Sector.
Government co-chairs the Nutrition Sector through the Civil Surgeon but is not active.
Sector Coordinators have a weekly meeting with Civil Military Coordination ( All sector Coordinators and the Military Camp Commanders)

## Slide 6: Additional Background
Before the crisis coordination of nutrition services:
  UNHCR - 2 Registered camps
  IOM - makeshift/spontaneous camps
IASC Cluster system not activated in August 2017
Nutrition Sector established in August 2017- Co-Led by Government and UNICEF
Complexities in camp management—UNHCR and IOM are “Camp Coordinating Agencies” managing the camp planning (except for the selection of the specific sector service providers) with different modus operandi.
Notes: Support received from Global level
Technical support from GNC at the onset of the response JRP development, Surge Capacity on coordination and information management
Joint call with key UN agencies
Higher level Advocacy e.g for use of RUTF for SAM treatment

## Slide 7: CMAM Programme Design
Due to the scale of need, initial priority for CMAM programme was rapid site establishment and scale up of the response.
Initial design was done in line with the 3 Key UN Mandates (WFP, UNHCR and UNICEF). The design was not coordinated and this led to a fragmented response.
The makeshift camp was initially (and some parts still are) very congested constraining access to nutrition services.
WFP BSFP under Food Security Cluster challenging continuum of care.
The design of the different components was based on the National CMAM guideline, which does not allow use of RUTF/RUSF and with a weak community out-reach component.

## Slide 8: Fragmentation of Nutrition Services
Notes: Different level of fragmentation
Same interventions e.g OTP implemented by different types of agencies in a single camp
CMAM services ( SAM and MAM) provided in different facilities in many camps in many cases run by different organizations

## Slide 9: Partnerships
Initial response heavily depended on NGOs existing in Cox Bazar prior to August 2017 due to lengthy NGO approval process by the Government.
UN agencies established partnerships with implementing partners based on convenience. WFP implementing Partners have to implement both TSFP and BSFP.
UNHCR and UNICEF separately established Partnerships in makeshift camps for SAM Treatment with similar agencies.
UNHCR/WFP and ACF had an existing tri-partite agreement to provided CMAM services for Registered camps before the crisis, but not for the makeshift camps.
No change in Partnership status quo for Stabilization Centers Services before and after the influx.
Notes: With no clear agreed mandates for CMAM in Country among the 3 UN agencies, there was some duplication in establishment of partnerships
WFP was not working in the makeshift camp before the influx.
ACF implementing SC services through Partnerships with both UNICEF and UNHCR. No other Partner implementing SC Services

## Slide 10: CMAM Programme Implementation
Initial targets for CMAM informed by Humanitarian Response Plan (HRP) and currently Joint Response Plan (JRP). Targets initially over-estimated which led to over-importation of RUTF.
No agreed modality for importation of RUTF among Key Pipeline agencies
Implementation guided by standards established in CMAM TWG. Until April 2018, no dedicated personnel to lead this function in the coordination Team.
Catchment areas for Nutrition Facilities were not clearly defined, leading to low coverage in some areas and overlapping services in others.
Due to an initial design that was made on individual CMAM components, integration of services remains a challenge for existing sites.
Notes: - The CMAM technical working group was established in September 2017,but with no dedicated long term chair. It was initially chaired by Concern Worldwide and then by World Concern. This was based on presence of technical staff well experienced in CMAM in the 2 agencies and their willingness to support the function.

## Slide 11: Progress So far
Identification of CMAM catchment areas and strategy for integration of services is on-going.
New and future Partnerships will be developed based on identified gaps from the above process.
Intra- and inter-sectoral integration agreed and implemented in new facilities in new camps (Health).
Establishment of Standard Operating Procedures for CMAM through the CMAM TWG - A work in progress.
Dedicated personnel for CMAM as part of Sector Coordination Team.
Notes: Having a dedicated CMAM Personnel has greatly contributed to harmonization and standardization pf practices across board, improved quality in service delivery through continuous hands on technical support and intra-inter-sectorial integration for CMAM.
Since this individual is seconded fully to the sector, he is seen as neutral and more widely accepted by Sector Partners.

## Slide 12: Camp 19 [Catchment Area]
Notes: Coordination improvement:
OTP of CWW in blue (at the lower part ) in Camp 13 and of TDH (slight green in Camp 19 have overlapping catchment areas (light green with blue stripes). The new maps enabled an agreement of all actors to assign Block A (black border in Camp 19 to the very left including a part in camp 20 ext) to CWW and Blocks B, C and D to TDH. ACF (yellow stripes in sub-bocks of Block A) agreed to close their OTP and move out due to low coverage.

## Slide 13: Ongoing-Challenges
Due to upcoming elections, the GoB has not moved from ‘emergency’ to a development response, making certain changes currently almost impossible.
Lengthy and complicated Government process for approvals of INGO projects.
Fragmentation of CMAM services still exists, quite difficult to undertake integration amidst complex challenges (Space, Topography).
While sector leadership is now widely accepted by Nutrition Sector Members, UNICEF Leadership Role as a Cluster Lead Agency needs to be further strengthened.
Government engagement and leadership role in the sector needs to be strengthened.
Various level of coordination. Camp In Charge (CiC) are very empowered and sometimes make un-consulted decisions.
Notes: Various levels of coordination and management
  UNHCR is Area Coordinating Agency and responsible to assign service providers for all sectors in their areas of jurisdiction, sometimes done without collaboration with sector coordination team.
  Camp in Charge (CiC = Local authority in charge of a camp) sometimes makes demands that can create serious problems (e.g. to close facilities for a few days for different reasons; provide staff to support Government surveys that might conflict with humanitarian principles; etc.)
  IPHN in Dhaka now requiring a lengthy approval process for Assessments, despite the Civil Surgeon agreeing
For I/NGOs an FD-6 project approval processes through the INGO Bureau is required before funding can be released. In the case of a non-emergency application approval takes up to 45 days; for a declared emergency, the commitment from the GoB is to turn it around within 48 hours. If a disaster is not declared, INGOs response may depend on their ability to use existing resources for up to 45 days.

## Slide 14: Lessons Learned
Provision of integrated services for CMAM should begin from the onset of the response and should be maintained in the entire project life cycle.
Global MoUs among UN agencies need to be effected and respected in new emergencies in the absence of Country Level MoUs.
Country Level MoUs among key UN agencies should be developed for disaster/emergency prone Countries and activated from the onset of emergencies.
Dedicated staff for sector Coordination and Key UN agencies should be available from the beginning of the response. Double hatting role of the Cluster/Sector Coordinator in large scale responses negatively affects neutrality and should be avoided at all costs.

## Slide 15: Lessons Learned
The success of Thematic TWGs in large scale emergencies heavily relies on having dedicated Human Resources, either provided by sector partners or CLA.
Coordination model for complex situations such as CXB to be re-examined and appropriate global guidance/coordination mechanism developed.
Estimation for supply needs for the collective response for new crisis needs to be developed based on complete evidence to avoid over or under estimation of supply needs.

## Slide 16: Discussion points
How can Countries manage when national guidance is not consistent with international recommendations/approach on CMAM as seen here?
Are there implications for the refugee coordination model, regarding overall coordination and thematic/sectoral coordination?
Do current global initiatives/international efforts by UN agencies currently in progress to support the continuum of care address the challenges we faced?
Are there other internationally recognized alternatives for SAM/MAM treatment in emergency contexts where use of RUTF/RUSF is not allowed?
Should Clusters include specific technical experts in addition to NCC and IMO?

## Slide 17: Group work
How can Countries manage when national guidance is not consistent with international recommendations/approach on CMAM as seen here?
    Are there other internationally recognized alternatives for SAM/MAM treatment in emergency contexts where use of RUTF/RUSF is not allowed?
How can we minimize disruption in continuum of care due to separate institutional responsibilities/approaches?

## Slide 18
THANK
YOU
bangladesh.nut@humanitarianresponse.info