## Sheet1
Objective/Result | Activity | Timeline | Comments | Budget | Lead | Indicators
Objective 1/ Result 1.1 | Develop a three year scale up plan, agreed with the partners and MoPHP | Sep - Dec 2018 | Led by UNCIEF WHO and WFP with NCC | Covered by existing programs | UNICEF (NCC when partner engagement is needed) | Three years scale up plan prepared and endorsed
Objective 1/ Result 1.1 | Develop PPT CMAM and lobbying by conducting coordination meetings with MoPHP, related UN agencies, partners, and nutriiton cluster to scale up CMAM for children U5 and PLW | Sep - Dec 2018 | To work directly with decesion makers for the scale up (MoPHP, UN agencies, Nutrition cluster) | Covered by existing programs | SAG | presentation developed and meetings with MoPHP, UN agencies, partners held
Objective 1/ Result 1.1 | Discussions with MoPHP towards full nutrition services to be free of charge, including TFC | Jan - March 2019 |  | Covered by existing programs | SAG, WHO, WFP, UNICEF | All nutrition sevices are free of charge
Objective 1/ Result 1.2 | Follow up with SAG and Nutrition Cluster partners to finalize SBC strategy | Sept - Oct 2018 |  | Covered by existing programs | Nutrtion Cluster Coordinator | SBCC stragegy endorsed
Objective 1/ Result 1.3 | Lobbying the MoPHP Nutrition Department to work in coordination with health authorities in the country for endorsment of nutrition and IYCF strategies | First 6 months of 2019 |  | Covered by existing programs | SAG , IYCF TWG | Nutrition and IYCF strategies endorsed
Objective 1/ Result 1.4 | Workshop to orient stakeholders on breastfeeding legislation and international code of marketing BMS | Quartely | These workshops will target different groups like: local authorities, nutriiton partners, local businesses. | tbc | MoPHP, UNICEF, WHO, SCI, IYCF TWG | Increased public support for breastfeeding across the country Reduction on Infant formula consumption in Yemen
Objective 1/ Result 1.5 | Lobyying to donors/Humanitarian Coordinator for fundraising efforts to support scale up in line with YHRP | 2018-2020 | Call for scaling up to cover the entire country by expanging the coverage for integrated package (joint statement, periodic bullitens, donors conferences) | tbc | Nutrition Cluster partners | % of fund allocated for scale up
Objective 2 / Result 2.1 | Ensure Nutriton Cluster SAG representation in SUN meetings working towards the development of multisectoral plan for nutrition with participation of relevant ministries and clusters | 2019 | Come up with outputs (package of integrated services, official agreement, timeline and plan for implementation) | tbc | Nutrition Cluster SAG | Nutrition-sensitive elements and priorities integrated and implemented as part of relevant sectoral policies and cluster plans
Objective 2 / Result 2.2 | Influence SUN to develop and widely dissemiante an advocacy paper on problems and gaps in funding to influence selected donors | Sep to Dec 2018 | Discuss with SUN gaps on information and influence the development of an advocacy paper | tbc | SUN | Policy paper finalised and target donors selected
Objective 2 / Result 2.1 | Ensure SAG representation (at least one person) in the other clusters (WASH, Health, FSAC) to allow linkages between the clusters and advocacy to them on behalf of the cluster partners | 2018-2020 | One -two people to represent NC at other clusters; meetings and feedback to the SAG | Covered by existing programs | Nutrition Cluster SAG | At least one nutiriton-sensitive interventions in WASH. Health and FSAC cluster included in the YHRP
Objective 3 / Result 3.1 | Review and update the existing incentives guideline for endorsement by cluster, MOPHP & Stakeholders and request GHO & DHO to monitore incentive rate by partners | Sep to Dec 2018 | Together with the Health Cluster and MoPHP health units | Covered by existing programs | Nutrition Cluster SAG | New guideline developed and endorsded by MoPHP and nutition cluster partners
Objective 3 / Result 3.1 | Conduct workshops among stakeholders and partners to introduce them to the new incentives guideline to ensure all partners follow it | 2018-12-01 |  |  | Nutiriton Cluster Coordinators at national and sub-national level | New guideline circulated among all nutrition partners and followed
Objective 3 / Result 3.2 | Develop advocacy/communication paper on the importance of adequate, timely and quality nutrition information for effective planning and prioritization (Cluster and MOPHP) and share with donors and other relevant actors | 2018 | Outline of advocacy/comms paper: 1- Avalible sources of nutrition information 2- Existing capacities for information collection, analysis, consolidation and dissemination 3- Implication of information gaps on nutrition planning and priorization; recource allocation 4- Ways forward |  | Lead: Techniqual Committee on SMARTs Potential supporting partners: MoPHP, UNICEF, WHO, SMART team hosted by ACF Canada, other country specific partners with expertise on assessments | Paper deveoped and shared with partners, MoPHP and donors
Objective 3 / Result 3.2 | High-level Advocacy workshop with key influential stakeholders, including donors and national government agencies presenting advocacy key messages on nutiriton information systems | End 2018/Early 2019 |  |  | Lead: MoPHP Supporting partners: Technical Comnittee on SMARTs | Workshop organised
Objective 3 / Result 3.2 | Based on adv/comms paper conclusions, develop and implement a stakeholders engagement strategy for strengthening Nutrition Information System within MoPHP at different level for data collection, analysis, consolidation and dissemination. | 2019-2020 | *See below further details on scope of stakeholders engagement strategy for strengthening Nutrition Information System |  | Lead: Techniqual Committee on SMART Potential supporting partners: MoPHP, UNICEF, WHO, SMART team hosted by ACF Canada, other country specific partners with expertise on assessments | Strategy developed and steps for implementation taken
Objective 3 / Result 3.3 to 3.4 | Develop and disseminate an advocacy paper highlighting capacity gaps and needs and strategy for capacity building | Sep 2018 - Dec 2018 - development of policy paper 2019 - develop strategy for capacity building and implementation 2019-2020 - implementation of capacity building strategy | Organise a workshop to develop the paper involving MOPHP, NGOs: 1- Map capacity gaps at different level by geographic locations 2- Gaps in capacity by nutrition interventions 3- Gaps by nutrition agencies 4- Identify budget and partners involvement for capacity building 5- Agree way forward and strategy for capacity building |  | CMAM TWG / IYCF TWG to work on the draft, finalised by the SAG | Advocacy paper developed and capacity buidling strategy for capacity building developed and iimplemented
Objective 3 / Result 3.5 | Advocacy for the SUN to implement a Nutriition day in Yemen and work with SUN on communication strategy to raise nutrition awareness on this day | Annually on the Nutriton Day | Through the available media channels, to encourage community participantion in the program implementation , breasfeeding week |  | UN agencies (UNICEF, WFP, WHO) | Nutrition Day implemented in Yemen/communication strategy with SUN developed/% of media stations involved
*Scope of stakeholders engagement strategy for strengthening Nutrition Information System:
a. Scope of Nutrition Information Management System at different levels (Central and Governorate)
a. Related task: In working sessions review exisiting tools, teams and capacity available within the system by the Technical Assessments Committee, potentially supported by relevant government agencies, UNICEF, SMART team and any other specific parnters with expertise on assessments.
b. Structure of information management team at central and governorate level of MoPHP based on the gaps identified in first paper
c. Technical capacity strengthening strategy or approaches to support MoPHP
c. Related task around b & c : Working session by Assessment Technical Committee; AWG members & SAG, M&E within nutrition department of MoPHP
d.Tentative Financial requirements to support the NIMS at central and Governorate level [in reference to the scope of the NIMS defined]
e. Phase-wise strategy for piloting and scaling up NIMS over a period of 3-5 years
f. Stakeholder mapping and engagement strategy for technical and operational support to MOPHP for establishment and strengthening of the NiMS
a. Related Tasks around d, e and f: Working sessions with Technical Committee on Assessment; AWG members; key partners and other relevant government actors in MoPHP related to Assessment.