## Slide 1
1. Finalized Inter-cluster Nutrition WG Training Package
Product
Purpose: finalize the ICNWG training package and make it available for interested countries
Activities undertaken:
Improved version with support of a training specialist – REdR
Review by partners
Translation to French
Progress:
Completed
Way forward:
- Make package available
Timeline: May 2019
Notes: Integrated Inter-cluster Training Package for Nutrition outcomes

## Slide 2
2. Country trainings on integrating nutrition
Product
Purpose: roll out the training in more countries
Activities undertaken:
3 country pilots
Evaluation of the trainings
Progress:
In progress
Timeline: December 2019
Way forward:
Trainings in DRC (05/2019), CAR (06/2019), WoS, Chad
Elaborate proposal for funding
Identify financial partners
Present in global cluster meetings (WASH / HEALTH) and in SUN

## Slide 3
3. Concept note on integrating nutrition
Product
Purpose: Raise funds to implement the planned activities
Activities undertaken:
- Concept note re-circulated and reviewed by the ICNWG;
- Technical and financial partners identified
Status:
In progress
Way forward:
- Continue discussion with potential partners.
Timeline: December 2019

## Slide 4
4. Case studies on integrating nutrition
Product
Purpose: Carry out country case studies on integrating nutrition
Activities undertaken:
Case studies included in the ICNWG concept note
Discussion with potential partners ongoing
ToR of the studies drafted and discussed
Progress:
In progress
Way forward (May 2019):
- Elaborate consultancy ToR (once funds confirmed)
Hire consultant
Initiate 1 country case
Timeline: December 2019

## Slide 5: Summary
Product 1. Finalized Inter-cluster Nutrition WG Training Package
Purpose: finalize the ICNWG training package and make it available for any interested countries
Product 2. Country trainings on integrating nutrition
Purpose: roll out the training in countries
Product 3. Concept note on integrating nutrition
December 2019
Purpose: Raise funds to implement the planned activities
Product 4. Case studies on integrating nutrition
December 2019
Purpose: Carry out country case studies on integrating nutrition
Trial period: support GTAM nutrition-sensitive thematic group
Completed
December 2019