**TIMELINE FOR JULY UPDATE OF COVID-19 GLOBAL HUMANITARIAN RESPONSE PLAN**

***As of 10 June 2020*-** Following endorsement by the IASC Principals, the next iteration of the GHRP will be launched on 16 July. This will be complemented by periodic progress reports to donors. After this next update, COVID-19 related needs and requirements will be gradually ‘folded’ into the 2021 HNOs and HRPs, and the GHRP will be transitioned to the Global Humanitarian overview to be issued early December.

**All deadlines are Geneva close-of-business time unless otherwise noted.**

| Issue | **Responsible** | **Deadline** |
| --- | --- | --- |
| **Initial outreach to RC/HCs**   * Country template * Information on monitoring framework | OCHA-USG | Friday 5 June |
| **Follow-up with RC/HCs and RCs**   * Formal transmission of final monitoring framework, and country inputs templates | OCHA-CD (CD Director to RC/HCs and RCs) | Wednesday 10 June/Thursday 11 June |
| **Annotated template of the GHRP Update, monitoring framework and country template**   * Transmission to IASC EDG and OPAG | OCHA/OAD and IASC Secretariat | Wednesday 10 June/Thursday 11 June |
| **Country inputs**   * Transmission to OCHA | OCHA/ UNHCR-IOM  (OCHA COs/ROs via OAD desks to APMB)  (UNHCR-IOM to APMB) | Monday 29 June |
| **Agency HQ inputs into the GHRP Update annotated template**   * Transmission to OCHA | EDG (one set of inputs per member or observer) | Monday 29 June |
| **Full draft of GHRP Update for agency red-line comments**   * Transmission to IASC EDG for comments | OCHA – CD (through EDG Chair and IASC Secretariat) | Tuesday 7 July |
|  |  |  |
| **Agency redline comments** of GHRP Update   * Transmission to OCHA | EDG (one set of inputs per member or observer) | Thursday 9 July |
| **Final GHRP launch** | OCHA | Thursday 16 July |