## Año
Año del plan de trabajo del Clúster de nutrición: AAAA
Objetivo del clúster | Actividad | Responsable del organismo | Organismos de apoyo | Clúster subnacional 1 | Clúster subnacional 2 | Clúster subnacional 3 | Indicador | Objetivo | Presupuesto total | Estado | T1 | T2 | T3 | T4 | Comentarios
Obj. 1 |  |  |  | Especificar la contribución de cada clúster subnacional a esta actividad o indicador | [5 empty] | Incluye una descripción breve del nivel de consecución; puede expresarse con códigos de color, de forma que el verde signifique que se están cumpliendo los objetivos de la actividad | Marcar con una X si la actividad debe completarse en este trimestre
Amarillo significa que la actividad está en curso, pero con ciertas limitaciones
Rojo significa que la actividad no se está implementando, tiene un retraso grave o no está logrando sus objetivos
Obj. 2
Obj. 3

## removed (hidden)
Cluster objective | Sub-cluster activities | Responsible & Lead | Indicator | Target | Total budget | UNICEF budget | WFP budget | WHO budget | other budget | Monitoring | Aden Hub | Sanaa Hub | Sadaa hub | Hudeidah hub | Ibb Hub | Q1 | Q2 | Q3 | Q4 | Status
| Carry out mass campaigns (30 episodes on 20 local tv stations during Ramadan, on radio, mass campaigns) | MoPHP, UNICEF UNICEF, QRCS | Number of episodes aired on TV station or radio Number of mass campaigns | 600 8 | [5 empty] | IYCF meeting minutes | N/A | N/A | N/A | N/A | N/A
| District monitors and districts assistants training on CMAM (Refresher training) - 3 days | CMAM TWG | Number of people trained | All districts | [6 empty] | All districts | All districts | All districts | All districts | All districts
| ToT for CHVs trainers on CMAM/IYCF/C4D - 6 days | CMAM TWG | Number of people trained | 480 trainers (20 trainers per governorate + 20 central) | [6 empty] | 160 | 120 | 40 | 80 | 40
| ToT for CHVs trainers on growth monitoring - 6 days | CMAM TWG | Number of people trained | 480 trainers (2o trainers per governorate + 20 central) | [6 empty] | 160 | 120 | 40 | 80 | 40
| ToT for HWs trainers on CMAM - 8 days | CMAM TWG | Number of people trained | 480 trainers (2o trainers per governorate + 20 central) | [6 empty] | 160 | 120 | 40 | 80 | 40
| ToT for HWs trainers on TFC/SC - 8 days | CMAM TWG | Number of people trained | 60 | [5 empty] | WHO | N/A | N/A | N/A | N/A | N/A
| ToT for IYCF trainers - 6 days | IYCF TWG | Number of people trained | 120 | [5 empty] | IYCF-WG | N/A | N/A | N/A | N/A | N/A
| Training of nutrition managers and focal points on IYCF at governorate & districts levels - 6 days | IYCF TWG | Number of people trained | 380 | [5 empty] | IYCF-WG | ??? | ??? | ??? | ??? | ???
| Sensitization workshops of the relevant stakeholders on the national legislations of breastfeeding protection & promotion - 1 day | IYCF TWG | Number of people trained | 500 | [6 empty] | ??? | ??? | ??? | ??? | ???
| CMAM sensitization sessions to be conducted targeting community leaders & influential people at district level | MoPHP, UNICEF & Ips | At least 1 session per district conducted per year | At least 1 session per district area conducted | 999000 |  | 0 | 0 |  | MoPHP, CMAM focal point in the MoPHP | XXX- number of districts | XXX- number of districts | XXX- number of districts | XXX- number of districts | XXX- number of districts | x | x | x | x
| Regular quarterly review meeting with the trained CHVs to be conducted | MoPHP, UNICEF & spartners | Number of CHV review meeting | Each CHV to participate in 1 review meeting per quarter (at least) | 5666666.6667 | 5100000 |  |  |  | Field Info template | tbc | tbc | tbc | tbc | tbc | x | x | x | x
| Develop guidelines for on job training (to be added to regular supporting supervision) | MoPHP, UNICEF, WFP & WHO | Guidelines for on job training developed and approved | Yes/no | 0 | 0 | 0 | 0 | 0 | Cluster meeting minutes | N/A | N/A | N/A | N/A | N/A
| CHVs training on growth monitoring - 5 days (according to MoPHP current schedule) To be updated when needed | CMAM TWG | Number of people trained | Priority districts (107 districts): 25% of the needs. Other districts: 7% of the needs | 3000000 | 2400000 |  |  |  | Field Info template | Priority districts (107 districts): 25% of the needs. Other districts: 10% of the needs | Priority districts (107 districts): 25% of the needs. Other districts: 10% of the needs | Priority districts (107 districts): 25% of the needs. Other districts: 10% of the needs | Priority districts (107 districts): 25% of the needs. Other districts: 10% of the needs | Priority districts (107 districts): 25% of the needs. Other districts: 10% of the needs
| CHWs training - 60 days | UNICEF | Number of people trained | tbc | [5 empty] | UNICEF | tbc | tbc | tbc | tbc | tbc
Note on F12: Anna Ziolkovska: 12,000 currently plus 10,000 new planned, 4 meetings per year, cost of 2000USD per one meeting which is attaended by 24 CHVs
Note on G12: Administrator: 90% For reviwe meeting will be supported by UNICEF